## Sheet1
Step | Time |  | 35 | 28.5714
Creating the database | 1 | 1
create the accounts table | 1 | 1
create the receipts table | 1 | 1
create accounts statement table | 1 | 1
create the vars table | 1 | 1
create users table | 1 | 1
create database abstraction layer | 2 | 2
create the accounts class | 1 | 1
create the vars calss | 1 | 1
create the statement class | 1
create receipts class | 1
create the vars class | 1
create the users class | 1
create the GUI project | 1
create a window for login | 1
create function for login | 1
create a function for getting list of accounts | 1
create user interface to display the list of accounts | 1
create a function to insert an account record | 1
create user interface for inserting a new account | 1
create a function for inserting a receipt into the database | 1
create gui for deposting money | 1
create gui for drawing money | 1
create gui for moving money | 1
create a function for recalculating receipts from a given date | 1
generate a report for account statement. | 1
create a backup function | 1
create restore function | 1
create ui for backup | 1
create ui for restore | 1
add modify receipt function | 1
add function for inserting new user | 1
add gui for inserting and listing users | 1
add a setup for the application | 1