## Sheet1
step no | details | time | done | total required | total done |  | functions
1 | design the db | 1 | 1 | 17 | 7 | 41.1765 | 1- user log into the system
2 | login | 1 | 1 |  |  |  | 2- user adds an item
3 | change password | 1 | 1 |  |  |  | 3- user edits an item
4 | view items | 1 | 1 |  |  |  | 4- user remove an item
5 | add item | 1 | 1 |  |  |  | 5- user fill a recipt
6 | edit item | 1 | 1 |  |  |  | 6- user display reports
7 | remove item | 1 | 1 |  |  |  | 7- user print a recipt
8 | add item to recipt | 1
9 | remove item from recipt | 1
10 | find recipt total | 1
11 | submit a recipt | 1
12 | display total sales for all time | 1
13 | display sales between two dates | 1
14 | draw recipt image | 1
15 | send the image to printer | 1
16 | backup | 1
17 | restore | 1
18 | create setup